## Project Schedule
CIVE 202 - Project #2: Automation of Concrete Mix Design
Mina Awad, Nick Meier, Owen Betts
Project Timeline: February 12 - February 24, 2026
TASK | ASSIGNED TO | START | END | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  |  |  | T | F | S | S | M | T | W | T | F | S | S | M | T
Project Management
Scope of Work | Mina Awad | 2026-02-12 | 2026-02-12 | bar: T; S to S; S to S
Gantt Chart | Nick Meier | 2026-02-12 | 2026-02-13 | bar: T to S; S to S
Excel Logic Analysis
Download & review NDOT workbook | Mina Awad | 2026-02-13 | 2026-02-14 | bar: F to S; S to S
Document formulas & cell mapping | Owen Betts | 2026-02-13 | 2026-02-14 | bar: F to S; S to S
Python Development
Core calculation functions (w/c, cement, water) | Mina Awad | 2026-02-15 | 2026-02-17 | bar: S to T; S to S
Aggregate proportioning functions | Nick Meier | 2026-02-15 | 2026-02-17 | bar: S to T; S to S
Sequential user input prompts | Owen Betts | 2026-02-17 | 2026-02-19 | bar: S to S; T to T; S to S
Output formatting (weight chart) | Nick Meier | 2026-02-18 | 2026-02-19 | bar: S to S; W to T; S to S
Mix Scenarios
Research & document scenarios 1 & 2 | Mina Awad | 2026-02-16 | 2026-02-18 | bar: S to W; S to S
Research & document scenarios 3 & 4 | Owen Betts | 2026-02-16 | 2026-02-18 | bar: S to W; S to S
Verification & Validation
Run 4 scenarios & compare results | Nick Meier | 2026-02-20 | 2026-02-21 | bar: S to S; F to S
Debug & resolve discrepancies | Mina Awad | 2026-02-20 | 2026-02-21 | bar: S to S; F to S
Documentation
Tech Report - Introduction & Methods | Mina Awad | 2026-02-19 | 2026-02-22 | bar: S to S; T to S
Tech Report - Results & Discussion | Nick Meier | 2026-02-20 | 2026-02-22 | bar: S to S; F to S
Annotated Code Document (ACD) | Owen Betts | 2026-02-19 | 2026-02-22 | bar: S to S; T to S
README & GitHub setup | Owen Betts | 2026-02-22 | 2026-02-23 | bar: S to S; S to M
Final Review & Submission
Final review, integration & submit | All | 2026-02-23 | 2026-02-24 | bar: S to S; S to T
Legend:
Mina Awad
Nick Meier
Owen Betts
All